## Sheet1
| Month |  |  | September | [29 empty] | October | [30 empty] | November
| Day |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
| Event | Duration | start
1 | Define problem | 1 | 2014-05-09
1.1 | Define a daily problem that a user may face to. | 1 | 2014-05-09
1.2 | Make a user story. | 1 | 2014-05-09
2 | Design solution | 7 | 2014-12-09
2.1 | Define the requirements for the program. | 1 | 2014-12-09
2.2 | Decide the implementation of the program abstractly. | 7 | 2014-12-09
2.2.1 | Members think about different implementation that can solve the problem. | 1 | 2014-12-09
2.2.2 | Discus about the Pros and Cons of each of the implementation method. | 1 | 2014-12-09
2.2.3 | Members decide which method will be used. | 7 | 2014-12-09
2.3 | Define set of function that need to be implemented. | 1 | 19/9/2014
2.4 | Decide the structure of the program | 1 | 19/9/2014
2.4.1 | Design Classes that can full fill each of the function's requirement. | 1 | 19/9/2014
2.4.2 | Build a class diagram that describe the relationship between each Class. | 1 | 19/9/2014
3 | start developing | 69 | 19/9/2014
3.1 | start developing for release 1 | 14 | 19/9/2014
3.1.1 | decide the functions that should include in release 1. | 1 | 19/9/2014
3.1.2 | Distribute task to each of the team member. | 1 | 19/9/2014
3.1.2.1 | Divide the project into smaller task sets. | 1 | 19/9/2014
3.1.2.2 | Distribute task set to members. | 1 | 19/9/2014
3.1.3 | Each member work on their task set. | 14 | 19/9/2014
3.2 | start developing for release 2 | 28 | 2014-03-10
3.2.1 | decide the functions that should include in release 2. | 1 | 2014-03-10
3.2.2 | Distribute task to each of the team member. | 1 | 2014-03-10
3.2.2.1 | Divide the project into smaller task sets. | 1 | 2014-03-10
3.2.2.2 | Distribute task set to members. | 1 | 2014-03-10
3.2.3 | Each member work on their task set. | 28 | 2014-03-10
3.3 | start developing for release 3 | 27 | 31/10/2014
3.3.1 | decide the functions that should include in release 3. | 1 | 31/10/2014
3.3.2 | Distribute task to each of the team member. | 1 | 31/10/2014
3.3.2.1 | Divide the project into smaller task sets. | 1 | 31/10/2014
3.3.2.2 | Distribute task set to members. | 1 | 31/10/2014
3.3.3 | Each member work on their task set. | 27 | 31/10/2014
4 | 4 Testing | 69 | 19/9/2014
4.1 | Testing for functions for release 1 | 14 | 19/9/2014
4.1.1 | Unit Test | 14 | 19/9/2014
4.1.1.1 | Build up test case base on the requirement. | 14 | 19/9/2014
4.1.1.2 | Get test cases running result. | 14 | 19/9/2014
4.1.1.3 | Report result to developer. | 14 | 19/9/2014
4.1.2 | System test
4.1.2.1 | Build up test case base on the requirement.
4.1.2.2 | Get test cases running result.
4.1.2.3 | Report result to developer.
4.2 | Testing for functions for release 2 | 28 | 2014-03-10
4.2.1 | Unit Test | 28 | 2014-03-10
4.2.1.1 | Build up test case base on the requirement. | 28 | 2014-03-10
4.2.1.2 | Get test cases running result. | 28 | 2014-03-10
4.2.1.3 | Report result to developer. | 28 | 2014-03-10
4.2.2 | System test | 28 | 2014-03-10
4.2.2.1 | Build up test case base on the requirement. | 28 | 2014-03-10
4.2.2.2 | Get test cases running result. | 28 | 2014-03-10
4.2.2.3 | Report result to developer. | 28 | 2014-03-10
4.3 | Testing for functions for release 3 | 27 | 31/10/2014
4.3.1 | Unit Test | 27 | 31/10/2014
4.3.1.1 | Build up test case base on the requirement. | 27 | 31/10/2014
4.3.1.2 | Get test cases running result. | 27 | 31/10/2014
4.3.1.3 | Report result to developer. | 27 | 31/10/2014
4.3.2 | System test | 27 | 31/10/2014
4.3.2.1 | Build up test case base on the requirement. | 27 | 31/10/2014
4.3.2.2 | Get test cases running result. | 27 | 31/10/2014
4.3.2.3 | Report result to developer. | 27 | 31/10/2014
5 | Deployment | 56 | 2014-03-10
5.1 | release 1 | 1 | 2014-03-10
5.2 | release 2 | 1 | 31/10/2014
5.3 | release 3 | 1 | 27/11/2014